## New Sheet
Primary Column | Column2 | Column3 | Column4 | Column5 | Column6
Task number | task name | start date | end date | Team member
1 | Architecture diagram | 2017-06-02 | 2017-06-04 | Kishan Patel, Achal Patel
2 | Project charter | 2017-06-01 | 2017-06-05 | Tom George
3 | Org chart | 2017-06-03 | 2017-06-04 | Dipankar Gosh
4 | Status Update | 2017-06-01 | 2017-06-06 | Kishan Patel
5 | Update architecture diagram | 2017-06-08 | 2017-06-11 | Kishan Patel
6 | Update project charter | 2017-06-08 | 2017-06-10 | Tom George
7 | Update org chart | 2017-06-09 | 2017-06-10 | Dipankar Gosh
8 | WBS | 2017-06-09 | 2017-06-12 | Kishan Patel,Achal Patel
9 | WBS Dictionary | 2017-06-14 | 2017-06-18 | Kishan Patel
10 | Updated WBS | 2017-06-14 | 2017-06-16 | Vinay Kulkarni, Achal Patel
11 | Updated Org chart | 2017-06-16 | 2017-06-19 | Dipankar Gosh
12 | Project gantt Chart | 2017-06-15 | 2017-06-20 | Tom George, Achal Patel
13 | Updated WBS Dictionary | 2017-06-24 | 2017-06-27 | Kishan Patel,
14 | Updated WBS | 2017-06-22 | 2017-06-25 | Kishan Patel, Achal Patel
15 | Updated Org chart | 2017-06-21 | 2017-06-23 | Dipankar Gosh
16 | Updated Project gantt Chart | 2017-06-23 | 2017-06-26 | Tom George, Achal Patel