## WBS
1 | Project plan creation and documentation
1.1 | Project charter
1.2 | Kickoff Meeting
1.3 | Requirements discussion & planning
1.4 | Planning the scope of the project
1.5 | Design project architecture
1.6 | Project management plan
1.7 | Constructing WBS
1.8 | Constructing WBS Dictionary
1.9 | Constructing the gantt chart
1.1 | Test plan documentation
2 | Project design
2.1 | Design project architecture
2.2 | Database schema design
3 | Design and development
3.1 | Server Setup
3.2 | Database setup
3.3 | Implementation
3.3.1 | Create project based on MVC
3.3.2 | Use MOQ libraries to write unit test
3.3.3 | Include a neat Bootstrapper template for the website
3.3.4 | Create a Layout page shared across various controllers and views
3.3.5 | Implement a top level AppController
3.3.6 | Configure services for logging in debug and production environment
3.3.7 | Include Entity Framework Core 1.0
3.3.7.1 | Create Entities, DbContext and use migrations
3.3.7.2 | Seed the Database
3.3.7.3 | Implement Repository pattern
3.3.7.4 | Add support for logging in the repository
3.3.7.5 | Automation testing: Write unit test code to test all methods in the data access layer
3.3.8 | Doctor Information services
3.3.8.1 | Implement controller for Doctor information services
3.3.8.2 | Create DoctorViewModel
3.3.8.3 | Cerate PatientViewModel
3.3.8.4 | Home page
3.3.8.5 | Appointments page
3.3.8.6 | Patient record page
3.3.8.7 | Entity framework: Implement the CRUD functionality
3.3.8.8 | Entity framework: Handle concurrency issues
3.3.8.9 | Add sorting, filtering functionality
3.3.8.10 | Add validation to the doctor model
3.3.8.11 | Add validation to the patient model
3.3.8.12 | Automation testing: Use MOQ to write code to test all controllers.
3.3.8.13 | Add search functionality
3.3.8.14 | Add support for logging
3.3.9 | Patient Information Services
3.3.9.1 | Implement controller for Patient infromation services
3.3.9.2 | Create Equipment viewmodel
3.3.9.3 | Create viewmodel fro bills
3.3.9.4 | Home page
3.3.9.5 | Appointments page
3.3.9.6 | View health records
3.3.9.7 | Available equipments
3.3.9.8 | Bill statements
3.3.9.9 | Entity framework: Implement the CRUD functionality
3.3.9.10 | Add sorting, filtering functionality
3.3.9.11 | Entity framework: Handle concurrency issues
3.3.9.12 | Automation testing: Use MOQ to write code to test all controllers.
3.3.9.13 | Add search functionality
3.3.9.14 | Add support for logging
3.3.10 | Staff Information Services
3.3.10.1 | Implement controller for Staff infromation services
3.3.10.2 | Home page
3.3.10.3 | Appointments page
3.3.10.4 | View health records
3.3.10.5 | Resource availability
3.3.10.6 | Billing transactions
3.3.10.7 | Entity framework: Implement the CRUD functionality
3.3.10.8 | Add sorting, filtering functionality
3.3.10.9 | Entity framework: Handle concurrency issues
3.3.10.10 | Automation testing: Use MOQ to write code to test all controllers.
3.3.10.11 | Add validation to models
3.3.10.12 | Add search functionality
3.3.10.13 | Add support for logging
3.3.11 | Resource Information Services
3.3.11.1 | Implement controller for resources information services
3.3.11.2 | Create viewmodels for the resource.
3.3.11.3 | Resource page
3.3.11.4 | Order page
3.3.11.5 | Billing transactions
3.3.11.6 | Entity framework: Implement the CRUD functionality
3.3.11.7 | Add sorting, filtering functionality
3.3.11.8 | Add validation to the resource model
3.3.11.9 | Automation testing: Use MOQ to write code to test all controllers.
3.3.11.10 | Entity framework: Handle concurrency issues
3.3.11.11 | Add search functionality
3.3.11.12 | Add support for logging
3.3.12 | Write SQL scheduler jobs to back up data every 3 months
3.3.13 | Finalizing Security Module
3.3.14 | Maintainance & change requests
4 | Testing
4.1 | Integration testing
4.2 | System testing
4.3 | Regression testing
4.4 | User acceptance testing
5 | Deployment
5.1 | Server
5.2 | Installation
5.3 | Roll out

## WBS Dictionary
1 | Project plan creation and documentation | This stage will include all the document gathering and planning processes
1.1 | Project charter | Creating Project charter
1.2 | Kickoff Meeting | Gathering of major stakeholders and discuss the project
1.3 | Requirements discussion & planning | Gathering of major stakeholder's requirements
1.4 | Planning the scope of the project | Discussing in scope and out scope of the project
1.5 | Design project architecture | Creating Project architecture diagram
1.6 | Project management plan | Formalizing project plan document and getting approval
1.7 | Constructing WBS | Discussing all the tasks involved
1.8 | Constructing WBS Dictionary | Defining all the tasks brief
1.9 | Constructing the gantt chart | Plan out the schedule of project
1.1 | Test plan documentation | Deciding and scheduling of different test cases
2 | Project design | This phase will include all the processes of specifying major modules and databases
2.1 | Design project architecture | Finalizing project modules and fine tuning the architecture
2.2 | Database schema design | Defining the schema and finding co relations among databases
3 | Design and development | This phase will include all the processes of actual implementation and setup of the website
3.1 | Server Setup | Configuring and activating server
3.2 | Database setup | Configuring and activating databases
3.3 | Implementation | This phase will include all the processes of actual implementation of the website
3.3.1 | Create project based on MVC | Design MVC structure for the project
3.3.2 | Use MOQ libraries to write unit test | Installing 3rd party libraries for automating unit testing
3.3.3 | Include a neat Bootstrapper template for the website | Download and setup bootstrap
3.3.4 | Create a Layout page shared across various controllers and views | Designed shared layout pages
3.3.5 | Implement a top level AppController | Create a controller which will handle which will handle common actions across various pages
3.3.6 | Configure services for logging in debug and production environment | Setup login framework
3.3.7 | Include Entity Framework Core 1.0 | Installing the entity framework ORM
3.3.7.1 | Create Entities, DbContext and use migrations | Defining specific Entities, DbContext and use migrations
3.3.7.2 | Seed the Database | Insert the dummy data for development
3.3.7.3 | Implement Repository pattern | Write code to define database interactions
3.3.7.4 | Add support for logging in the repository | Write code to log information/errors in the repository layer
3.3.7.5 | Automation testing: Write unit test code to test all methods in the data access layer | Write unit test code to test all methods
3.3.8 | Doctor Information services | This stage contains all the processes related to designing doctor’s portal.
3.3.8.1 | Implement controller for Doctor information services | Write code to handle actions from doctor's portal
3.3.8.2 | Create DoctorViewModel | Create class to bind doctor's data with the GUI
3.3.8.3 | Cerate PatientViewModel | Create class to bind patient's data with the doctor's GUI
3.3.8.4 | Home page | Create a home page for doctors that will show doctor’s today’s appointments and also links to other pages described below.
3.3.8.5 | Appointments page | This page will go to personnel database and get all the schedules and appointments details for the currently logged in doctor.
3.3.8.6 | Patient record page | This page will list all the patients and their details, treated by doctor. And also provide a way to update anyone of them.
3.3.8.7 | Entity framework: Implement the CRUD functionality | Write code to handle crud operations from doctor's portal
3.3.8.8 | Entity framework: Handle concurrency issues | Handle simultaneous usage scenarios
3.3.8.9 | Add sorting, filtering functionality | Creating sorting and filtering functionality on the listed items
3.3.8.10 | Add validation to the doctor model | Write a code to validate the doctor data before processing
3.3.8.11 | Add validation to the patient model | Write a code to validate the patient data before processing
3.3.8.12 | Automation testing: Use MOQ to write code to test all controllers. | Use MOQ to write unit test for all the methods in controller
3.3.8.13 | Add search functionality | Create data search functionality, required by doctor
3.3.8.14 | Add support for logging | Write code to log information/errors
3.3.9 | Patient Information Services | This stage contains all the processes related to designing patient’s portal.
3.3.9.1 | Implement controller for Patient infromation services | Write code to handle actions from patient's portal
3.3.9.2 | Create Equipment viewmodel | Create class to bind equipment's data with the patients' GUI
3.3.9.3 | Create viewmodel fro bills | Create class to bind bill's data with the patients' GUI
3.3.9.4 | Home page | Create a home page for patient’s that will show patient’s upcoming appointments and also links to other pages described below.
3.3.9.5 | Appointments page | This page will show all the appointment records of this patient from patients’ database.
3.3.9.6 | View health records | This page will show all the health records of this patient from patients’ database.
3.3.9.7 | Available equipments | This page will show all the equipment’s and their availability from resources database
3.3.9.8 | Bill statements | This page will show all the billing records of this patient from patients’ database.
3.3.9.9 | Entity framework: Implement the CRUD functionality | Write code to handle crud operations from patient's portal
3.3.9.10 | Add sorting, filtering functionality | Creating sorting and filtering functionality on the listed items
3.3.9.11 | Entity framework: Handle concurrency issues | Handle simultaneous usage scenarios
3.3.9.12 | Automation testing: Use MOQ to write code to test all controllers. | Use MOQ to write unit test for all the methods in controller
3.3.9.13 | Add search functionality | Create data search functionality, required by patients'
3.3.9.14 | Add support for logging | Write code to log information/errors
3.3.10 | Staff Information Services | This stage contains all the processes related to designing staff’s portal.
3.3.10.1 | Implement controller for Staff infromation services | Write code to handle actions from staff's portal
3.3.10.2 | Home page | Create a home page for staff that will show staff’s today’s schedule and also links to other pages described below.
3.3.10.3 | Appointments page | This page will show all the appointment of doctor or patient as per requested.
3.3.10.4 | View health records | This page will show all the health records of this patient from patients’ database.
3.3.10.5 | Resource availability | This page will show all the resources and their availability and they can also request for such resources.
3.3.10.6 | Billing transactions | This page is for the billing transaction of specific patient.
3.3.10.7 | Entity framework: Implement the CRUD functionality | Write code to handle crud operations from staff's portal
3.3.10.8 | Add sorting, filtering functionality | Creating sorting and filtering functionality on the listed items
3.3.10.9 | Entity framework: Handle concurrency issues | Handle simultaneous usage scenarios
3.3.10.10 | Automation testing: Use MOQ to write code to test all controllers. | Use MOQ to write unit test for all the methods in controller
3.3.10.11 | Add validation to models | Write a code to validate the staff's data before processing
3.3.10.12 | Add search functionality | Create data search functionality, required by staff
3.3.10.13 | Add support for logging | Write code to log information/errors
3.3.11 | Resource Information Services | This stage contains all the processes related to designing resources’ portal.
3.3.11.1 | Implement controller for resources information services | Write code to handle actions from resource's portal
3.3.11.2 | Create viewmodels for the resource. | Create class to bind bill's data with the resources' GUI
3.3.11.3 | Resource page | This page will show all the resources and their availability.
3.3.11.4 | Order page | Through this page the user can order specific resources.
3.3.11.5 | Billing transactions | Final billing transaction page for resources.
3.3.11.6 | Entity framework: Implement the CRUD functionality | Write code to handle crud operations from resource's portal
3.3.11.7 | Add sorting, filtering functionality | Creating sorting and filtering functionality on the listed items
3.3.11.8 | Add validation to the resource model | Write a code to validate the resources's data before processing
3.3.11.9 | Automation testing: Use MOQ to write code to test all controllers. | Use MOQ to write unit test for all the methods in controller
3.3.11.10 | Entity framework: Handle concurrency issues | Handle simultaneous usage scenarios
3.3.11.11 | Add search functionality | Create data search functionality, required by resource portal
3.3.11.12 | Add support for logging | Write code to log information/errors
3.3.12 | Write SQL scheduler jobs to back up data every 3 months | Write SQL scripts to backup database every 3 months
3.3.13 | Finalizing Security Module | Final review of security module
3.3.14 | Maintainance & change requests | Collect maintenance and change requests
4 | Testing | This stage contains all the processes related to testing phase.
4.1 | Integration testing | Integrate various modules and apply test cases
4.2 | System testing | Test the whole system under different scenario
4.3 | Regression testing | perform regressive testing
4.4 | User acceptance testing | Give end user's to test the system on their own
5 | Deployment | This stage includes all the processes related to deploy website on actual web. Make the website live.
5.1 | Server | Buying server space and hosting plan
5.2 | Installation | Installing website code in the hosting environment
5.3 | Roll out | Make the website live.